## Lists
Not Started | Must Have | Functional | Foundation | superadmin
In Progress | Should Have | Non-Functional | Core Build | admin
Blocked | Could Have | Data | Admin & Security | manager
Done |  | Security | Hardening | user
|  | UX | Release

## README
Python Desktop Application - SRS and Delivery Plan
Prepared For | Desktop application with PostgreSQL + Liquibase, authentication, RBAC, and future extensibility
Assumed Project Start (editable) | 2026-04-07
Recommended UI Stack | PySide6 (Qt for Python) for a professional native desktop UI
Migration Strategy | Liquibase changelogs managed separately from Python application code
Architecture Style | Modular layered architecture: presentation, application, domain, infrastructure
Project Snapshot
Total requirements | 21
Functional requirements | 14
Non-functional/data/security/ux requirements | 7
Total milestones | 6
Total planned tasks | 22
Total planned effort (days) | 35
Projected finish date | 2026-05-11
Total AI prompts prepared | 16
How to Use This Workbook
• | Requirements sheet captures functional and non-functional expectations with acceptance criteria.
• | Roles_Permissions defines the baseline RBAC model and the suggested permission catalog.
• | DB_Schema provides a normalized PostgreSQL schema designed for future feature growth.
• | Liquibase_Plan organizes the initial database migrations and rollback expectations.
• | Milestones and Plan provide a practical implementation roadmap; change the project start on this sheet if needed.
• | Prompts contains copy/paste prompts for incremental development tasks.

## SRS
Software Requirements Specification
1. Purpose | Build a maintainable desktop application in Python with a professional user interface, PostgreSQL persistence, Liquibase-based schema versioning, secure login using username or mobile number with password, and a configurable role-based access control model.
2. In Scope | Authentication, user administration, role and permission management, normalized database design, auditability, future-ready modular architecture, and planning for incremental delivery.
3. Out of Scope (initial release) | Advanced SSO, biometric login, multi-tenant isolation, external identity providers, fine-grained field masking, reporting warehouse, and mobile app support.
4. Primary Actors | Superadmin, Admin, Manager, End User, Support/Operations.
5. Business Goals | Secure application access, delegated administration, controlled feature access through RBAC, easy future extension, and a polished desktop user experience.
6. Recommended Technical Stack | UI: PySide6. Backend/application layer: Python 3.11+ service modules. ORM/data access: SQLAlchemy 2.x. Database: PostgreSQL 15+. Migrations: Liquibase XML/YAML/SQL changelogs. Packaging: PyInstaller or Briefcase.
7. Security Expectations | Passwords stored as strong salted hashes (Argon2id or bcrypt), account lockout policy, password change tracking, audit logging, and secure secret handling outside source control.
8. Extensibility Expectations | Use modular packages, configuration-driven permissions, additive Liquibase changesets, and service interfaces so new modules can be plugged in later without redesigning the core schema.
9. Usability Expectations | Responsive forms, clear error messages, keyboard-friendly data entry, role-aware navigation, and consistent visual styling across screens.
10. Success Criteria | Users can authenticate by username or mobile, admins can create/update roles and permissions, permissions are enforced in the UI and backend, schema is migration-controlled, and the codebase can accommodate new business modules.
Suggested Application Modules
Module | Responsibility
Presentation | Desktop screens, dialogs, forms, dashboards, validation feedback
Application | Use cases, workflows, RBAC checks, orchestration services
Domain | User, Role, Permission, Audit, Session, Settings rules
Infrastructure | PostgreSQL repositories, Liquibase execution, logging, packaging
Security | Password hashing, lockout, session lifecycle, permission guards
Administration | User management, role management, permission catalog management

## Requirements
Requirements Register
Req ID | Type | Module | Requirement | Acceptance Criteria | Priority | Phase | Notes
FR-01 | Functional | Authentication | User can log in with either username or registered mobile number plus password. | Login succeeds when valid identifier/password pair is provided; invalid attempts show safe error message. | Must Have | Foundation | Support multiple identifier types through normalized login_identifiers table.
FR-02 | Functional | Authentication | System must validate account status before login. | Inactive, locked, or disabled accounts cannot access the application. | Must Have | Foundation | Supports security control and admin actions.
FR-03 | Functional | Security | Passwords must be stored as salted secure hashes. | No plain-text password is stored anywhere in database or logs. | Must Have | Foundation | Use Argon2id or bcrypt.
FR-04 | Functional | Authorization | System must support configurable roles such as superadmin, admin, manager, and user. | Default roles exist at setup and can be assigned to users. | Must Have | Foundation | Roles should be data-driven.
FR-05 | Functional | Authorization | Permissions must be assignable to roles and enforced by the application. | Access to screens/actions is blocked when required permission is missing. | Must Have | Core Build | RBAC must be checked in UI and service layer.
FR-06 | Functional | Administration | Authorized admins can create, update, activate, and deactivate users. | Changes are persisted and visible in user management screens. | Must Have | Core Build | Soft delete preferred for auditability.
FR-07 | Functional | Administration | Authorized admins can create, update, activate, and deactivate roles. | Role changes are reflected immediately in access rules after assignment. | Must Have | Core Build | Protect system roles from unsafe deletion.
FR-08 | Functional | Administration | Authorized admins can create and modify permission definitions. | New permissions can be added without changing core user table structure. | Should Have | Core Build | Catalog management may be admin-only.
FR-09 | Functional | Administration | Authorized admins can map permissions to roles. | Role-permission assignments can be added or removed through UI. | Must Have | Core Build | Store in role_permissions junction table.
FR-10 | Functional | Administration | Authorized admins can assign multiple roles to a single user. | A user can inherit permissions from all assigned active roles. | Should Have | Core Build | Many-to-many user_roles table.
FR-11 | Functional | Audit | System must record key administrative and authentication events. | Login success/failure, user changes, role changes, and permission changes are logged. | Must Have | Admin & Security | Store summary and before/after JSON where appropriate.
FR-12 | Functional | Security | System should lock the account temporarily after repeated failed logins. | Lockout threshold and duration are configurable. | Should Have | Admin & Security | Configuration-driven control.
FR-13 | Functional | Session | System should maintain application session metadata. | Last login time and current active session details can be tracked. | Could Have | Admin & Security | Useful for audit and support.
FR-14 | Functional | Configuration | System should support application settings for future modules. | Config values can be stored and managed without schema redesign. | Could Have | Hardening | Use key-value or scoped settings table.
NFR-01 | Non-Functional | Usability | Application UI must feel professional, consistent, and easy to navigate. | Users can access primary actions within three clicks; forms show clear labels and feedback. | Must Have | Foundation | Use consistent theme and layout.
NFR-02 | Non-Functional | Performance | Common screens should load within acceptable desktop-app response time. | Login and standard CRUD screens respond within 2 seconds under normal load. | Should Have | Hardening | Performance target should be validated.
NFR-03 | Security | Security | Sensitive data must be protected in transit and at rest where applicable. | Database credentials stored securely; password hashes and audit controls implemented. | Must Have | Foundation | No secrets in source control.
NFR-04 | Non-Functional | Maintainability | Codebase must be modular so new features can be added later. | New feature module can be added without modifying unrelated core modules. | Must Have | Foundation | Layered architecture and clear contracts.
NFR-05 | Data | Database | Database schema must be normalized and migration-controlled. | Schema changes are introduced only through Liquibase changesets. | Must Have | Foundation | Target 3NF for master/transaction data.
NFR-06 | Non-Functional | Reliability | Application should recover gracefully from database and validation errors. | User sees actionable message; app remains stable; exception is logged. | Should Have | Hardening | Standardized exception handling.
NFR-07 | UX | Accessibility | Forms and navigation should support keyboard usage and readable typography. | Primary workflows can be executed with keyboard-only navigation. | Could Have | Hardening | Improves desktop productivity.

## Roles_Permissions
RBAC Model - Roles and Permissions
Default Roles
Role | Purpose | Can Manage Users | Can Manage Roles/Permissions | Notes
superadmin | Full system administration and recovery actions | Yes | Yes | System-level role; should be protected from accidental deactivation.
admin | Operational administration and day-to-day configuration | Yes | Yes | Can manage users and business roles under policy.
manager | Business supervision with limited administrative rights | Limited | No | Typically manages business operations and approvals.
user | Standard application user | No | No | Access only to assigned business functions.
Suggested Permission Catalog and Default Assignment
Permission Code | Business Meaning | Module | superadmin | admin | manager | user | Priority | Notes
auth.login | Access application login flow | Authentication | Y | Y | Y | Y | Must Have | Granted to all active users.
user.view | View user list and profile details | Administration | Y | Y | N | N | Must Have | Admin area visibility.
user.create | Create a user account | Administration | Y | Y | N | N | Must Have | Create flow.
user.update | Edit user account profile/status | Administration | Y | Y | N | N | Must Have | Includes activation/deactivation.
user.assignRoles | Assign roles to users | Administration | Y | Y | N | N | Must Have | Critical RBAC control.
role.view | View roles and mappings | Administration | Y | Y | N | N | Must Have | Role catalog read.
role.create | Create a role | Administration | Y | Y | N | N | Should Have | Data-driven role management.
role.update | Modify role definition | Administration | Y | Y | N | N | Must Have | Should block unsafe system-role changes.
role.delete | Deactivate or remove a non-system role | Administration | Y | Limited | N | N | Could Have | Prefer deactivate over hard delete.
permission.view | View permission catalog | Administration | Y | Y | N | N | Must Have | Supports audits.
permission.create | Create permission definitions | Administration | Y | Limited | N | N | Should Have | Often reserved for higher admins.
permission.update | Update permission definitions | Administration | Y | Limited | N | N | Should Have | Careful change control needed.
rolePermission.manage | Map permissions to roles | Administration | Y | Y | N | N | Must Have | Central RBAC operation.
audit.view | Review audit logs | Audit | Y | Y | Limited | N | Should Have | Visibility may be scoped by policy.
settings.manage | Manage application settings | Configuration | Y | Limited | N | N | Could Have | Useful for future features.

## DB_Schema
Normalized PostgreSQL Schema (3NF-oriented)
Table | Column | Data Type | PK | FK | Unique | Null? | Default | Purpose / Rule | Relationship Notes
users | user_id | BIGSERIAL | Y |  | Y | N |  | Surrogate primary key | Parent table for identities, roles, audit
users | first_name | VARCHAR(100) |  |  |  | N |  | User given name
users | last_name | VARCHAR(100) |  |  |  | Y |  | User family name
users | display_name | VARCHAR(150) |  |  |  | Y |  | Friendly UI name
users | status | VARCHAR(20) |  |  |  | N | 'ACTIVE' | ACTIVE/INACTIVE/LOCKED
users | created_at | TIMESTAMP |  |  |  | N | now() | Audit timestamp
users | updated_at | TIMESTAMP |  |  |  | N | now() | Audit timestamp
login_identifiers | identifier_id | BIGSERIAL | Y |  | Y | N |  | PK for login identifiers | Child of users (1-to-many)
login_identifiers | user_id | BIGINT |  | users.user_id |  | N |  | Owner user | Many identifiers per user
login_identifiers | identifier_type | VARCHAR(20) |  |  |  | N |  | USERNAME / MOBILE
login_identifiers | identifier_value | VARCHAR(150) |  |  |  | N |  | Original value entered by admin/user
login_identifiers | normalized_value | VARCHAR(150) |  |  | Y | N |  | Case/format normalized lookup value | Unique login key across system
login_identifiers | is_primary | BOOLEAN |  |  |  | N | false | Preferred login/display identifier
login_identifiers | is_verified | BOOLEAN |  |  |  | N | false | Supports future OTP/verification flows
auth_credentials | credential_id | BIGSERIAL | Y |  | Y | N |  | PK for auth record | 1-to-1 with users
auth_credentials | user_id | BIGINT |  | users.user_id | Y | N |  | One credential record per user
auth_credentials | password_hash | VARCHAR(255) |  |  |  | N |  | Salted password hash only
auth_credentials | password_algo | VARCHAR(30) |  |  |  | N | 'argon2id' | Hash algorithm marker
auth_credentials | password_changed_at | TIMESTAMP |  |  |  | Y |  | Password lifecycle audit
auth_credentials | failed_attempt_count | INT |  |  |  | N | 0 | Support lockout logic
auth_credentials | locked_until | TIMESTAMP |  |  |  | Y |  | Temporary lock expiration
auth_credentials | last_login_at | TIMESTAMP |  |  |  | Y |  | User last successful login
roles | role_id | BIGSERIAL | Y |  | Y | N |  | PK for roles | Parent table for user_roles and role_permissions
roles | role_code | VARCHAR(50) |  |  | Y | N |  | Stable code, e.g. ADMIN
roles | role_name | VARCHAR(100) |  |  |  | N |  | Display label
roles | description | TEXT |  |  |  | Y |  | Business meaning
roles | is_system_role | BOOLEAN |  |  |  | N | false | Protect built-in roles
roles | is_active | BOOLEAN |  |  |  | N | true | Soft lifecycle
permissions | permission_id | BIGSERIAL | Y |  | Y | N |  | PK for permissions | Parent for role_permissions
permissions | permission_code | VARCHAR(100) |  |  | Y | N |  | Stable code, e.g. user.create
permissions | module_name | VARCHAR(100) |  |  |  | N |  | Functional grouping
permissions | action_name | VARCHAR(100) |  |  |  | N |  | View/Create/Update/Delete/etc.
permissions | description | TEXT |  |  |  | Y |  | Business meaning
permissions | is_active | BOOLEAN |  |  |  | N | true | Soft lifecycle
user_roles | user_role_id | BIGSERIAL | Y |  | Y | N |  | Surrogate PK | Junction table users ↔ roles
user_roles | user_id | BIGINT |  | users.user_id |  | N |  | Assigned user
user_roles | role_id | BIGINT |  | roles.role_id |  | N |  | Assigned role
user_roles | assigned_by | BIGINT |  | users.user_id |  | Y |  | Admin who assigned role
user_roles | assigned_at | TIMESTAMP |  |  |  | N | now() | Assignment timestamp
user_roles | is_active | BOOLEAN |  |  |  | N | true | Supports historical role mapping | Unique(user_id, role_id, is_active) by policy
role_permissions | role_permission_id | BIGSERIAL | Y |  | Y | N |  | Surrogate PK | Junction table roles ↔ permissions
role_permissions | role_id | BIGINT |  | roles.role_id |  | N |  | Role owner
role_permissions | permission_id | BIGINT |  | permissions.permission_id |  | N |  | Permission granted
role_permissions | granted_at | TIMESTAMP |  |  |  | N | now() | Audit timestamp
role_permissions | granted_by | BIGINT |  | users.user_id |  | Y |  | Admin who granted permission | Unique(role_id, permission_id)
user_sessions | session_id | UUID | Y |  | Y | N |  | Track active desktop sessions | Child of users (1-to-many)
user_sessions | user_id | BIGINT |  | users.user_id |  | N |  | Session owner
user_sessions | login_at | TIMESTAMP |  |  |  | N | now() | Session start
user_sessions | logout_at | TIMESTAMP |  |  |  | Y |  | Session end
user_sessions | client_info | VARCHAR(255) |  |  |  | Y |  | Machine/app metadata
user_sessions | is_active | BOOLEAN |  |  |  | N | true | Current session flag
audit_logs | audit_id | BIGSERIAL | Y |  | Y | N |  | PK for audit events | Child of users (many-to-one actor)
audit_logs | actor_user_id | BIGINT |  | users.user_id |  | Y |  | User causing change/event
audit_logs | event_type | VARCHAR(100) |  |  |  | N |  | LOGIN_SUCCESS, ROLE_UPDATED, etc.
audit_logs | entity_name | VARCHAR(100) |  |  |  | Y |  | Affected entity/table concept
audit_logs | entity_id | VARCHAR(100) |  |  |  | Y |  | Affected record identifier
audit_logs | before_state_json | JSONB |  |  |  | Y |  | Before snapshot
audit_logs | after_state_json | JSONB |  |  |  | Y |  | After snapshot
audit_logs | created_at | TIMESTAMP |  |  |  | N | now() | Event time
app_settings | setting_id | BIGSERIAL | Y |  | Y | N |  | PK for app settings | Supports future features
app_settings | setting_key | VARCHAR(100) |  |  | Y | N |  | Unique config key
app_settings | setting_value | TEXT |  |  |  | Y |  | Stored value
app_settings | scope | VARCHAR(30) |  |  |  | N | 'GLOBAL' | GLOBAL/ROLE/USER
app_settings | scope_ref_id | BIGINT |  |  |  | Y |  | Optional scope target
Relationship Summary
Relationship | Cardinality | Why It Exists | Design Note
users -> login_identifiers | 1 : many | Supports login by username, mobile, and future identifiers | Enforce uniqueness on normalized_value.
users -> auth_credentials | 1 : 1 | Separates identity from credential storage | Keeps auth concerns isolated.
users -> user_roles | 1 : many | Allows one user to hold multiple roles | Supports composite access.
roles -> user_roles | 1 : many | Maps reusable roles to many users | RBAC core.
roles -> role_permissions | 1 : many | Assigns many permissions to a role | Data-driven authorization.
permissions -> role_permissions | 1 : many | Each permission can be reused by many roles | Avoids duplicated permission definitions.
users -> audit_logs | 1 : many | Tracks who performed an action | Critical for traceability.

## Liquibase_Plan
Liquibase Migration Plan
Order | ChangeSet ID | Change Type | Objects | Purpose | Rollback Strategy | Notes
1 | 001-create-core-users | createTable | users | Create base user master table | dropTable users | Establishes identity root.
2 | 002-create-login-identifiers | createTable | login_identifiers | Support username/mobile login identifiers | dropTable login_identifiers | Add unique index on normalized_value.
3 | 003-create-auth-credentials | createTable | auth_credentials | Store password hash and lockout metadata | dropTable auth_credentials | Separate credentials from profile.
4 | 004-create-roles | createTable + loadData | roles | Create role master and seed default roles | delete seed rows / dropTable | Seed superadmin, admin, manager, user.
5 | 005-create-permissions | createTable + loadData | permissions | Create permission catalog and seed baseline permissions | delete seed rows / dropTable | Seed only core permissions first.
6 | 006-create-user-roles | createTable | user_roles | Map users to roles | dropTable user_roles | Add unique composite rule.
7 | 007-create-role-permissions | createTable | role_permissions | Map roles to permissions | dropTable role_permissions | Central RBAC mapping.
8 | 008-create-user-sessions | createTable | user_sessions | Track login sessions | dropTable user_sessions | Optional in first release; can still be included.
9 | 009-create-audit-logs | createTable | audit_logs | Track security and admin events | dropTable audit_logs | Use JSONB snapshots for before/after.
10 | 010-create-app-settings | createTable | app_settings | Store future-ready config items | dropTable app_settings | Supports extensibility without redesign.
11 | 011-add-indexes | createIndex | login_identifiers, user_roles, role_permissions, audit_logs | Improve lookup and enforcement performance | dropIndex | Index normalized_value and FK columns.
12 | 012-add-constraints | addForeignKeyConstraint / addUniqueConstraint | core RBAC tables | Enforce relational integrity | drop constraints | Keep schema consistent across environments.

## Milestones
Milestones
Milestone ID | Milestone | Goal | Start Date | Duration (days) | End Date | Exit Criteria
M1 | Foundation & Architecture | Finalize stack, project structure, security baseline, and schema design | 2026-04-07 | 5 | 2026-04-11 | Architecture approved; schema and SRS signed off.
M2 | Database & Migration Baseline | Implement PostgreSQL schema and Liquibase changelogs | 2026-04-12 | 5 | 2026-04-16 | Liquibase baseline runs clean on local and test DB.
M3 | Authentication Module | Deliver login with username/mobile and secure credential flow | 2026-04-17 | 6 | 2026-04-22 | Login flow works with validation and lockout basics.
M4 | RBAC & Admin Module | Deliver role, permission, and user-role management | 2026-04-23 | 8 | 2026-04-30 | Admins can manage roles/permissions and user assignments.
M5 | Audit, Hardening & UX Polish | Add audit trail, error handling, and UI polish | 2026-05-01 | 6 | 2026-05-06 | Audit log and user-friendly validation are completed.
M6 | Testing, Packaging & Release Prep | Stabilize, test, package, and document the release | 2026-05-07 | 5 | 2026-05-11 | Acceptance tests passed and desktop package generated.
Formulas:
End Date = [Start Date]+[Duration (days)]-1

## Plan
Detailed Implementation Plan
Task ID | Milestone | Task | Effort (days) | Owner | Planned Start | Planned End | Dependency | Deliverable | Status
T01 | M1 | Finalize architecture, stack, coding standards, and repository layout | 1 | Architect | 2026-04-07 | 2026-04-07 | - | Approved architecture note | Not Started
T02 | M1 | Prepare SRS, screen list, and data flow decisions | 1 | BA/Architect | 2026-04-08 | 2026-04-08 | T01 | Approved SRS and flow summary | Not Started
T03 | M1 | Design normalized PostgreSQL schema and RBAC model | 2 | DB Engineer | 2026-04-09 | 2026-04-10 | T02 | Reviewed ERD/schema specification | Not Started
T04 | M1 | Set up project scaffold with modular folders and environment config | 1 | Python Dev | 2026-04-11 | 2026-04-11 | T01 | Working starter project | Not Started
T05 | M2 | Create Liquibase master changelog and baseline changesets | 2 | DB Engineer | 2026-04-12 | 2026-04-13 | T03 | Baseline changelog files | Not Started
T06 | M2 | Provision PostgreSQL local/test environments and validate migrations | 1 | DevOps/DBA | 2026-04-14 | 2026-04-14 | T05 | Database bootstrap script | Not Started
T07 | M2 | Implement ORM models and repository interfaces | 2 | Python Dev | 2026-04-15 | 2026-04-16 | T05 | Data access layer | Not Started
T08 | M3 | Build login screen with username/mobile identifier input | 1 | UI Dev | 2026-04-17 | 2026-04-17 | T04 | Desktop login UI | Not Started
T09 | M3 | Implement authentication service and password verification | 2 | Python Dev | 2026-04-18 | 2026-04-19 | T07 | Auth service | Not Started
T10 | M3 | Add lockout, failed-attempt tracking, and secure session start | 2 | Python Dev | 2026-04-20 | 2026-04-21 | T09 | Security controls | Not Started
T11 | M3 | Wire login UI to backend and database | 1 | Full-stack Dev | 2026-04-22 | 2026-04-22 | T08,T09 | End-to-end login flow | Not Started
T12 | M4 | Create user management screens and CRUD workflows | 2 | UI/Backend Dev | 2026-04-23 | 2026-04-24 | T07 | User administration feature | Not Started
T13 | M4 | Create role management screens and service layer | 2 | UI/Backend Dev | 2026-04-25 | 2026-04-26 | T07 | Role administration feature | Not Started
T14 | M4 | Create permission catalog and role-permission mapping workflows | 2 | UI/Backend Dev | 2026-04-27 | 2026-04-28 | T13 | Permission administration feature | Not Started
T15 | M4 | Implement RBAC guards in navigation, screens, and services | 2 | Python Dev | 2026-04-29 | 2026-04-30 | T12,T13,T14 | Permission enforcement layer | Not Started
T16 | M5 | Implement audit logging for login and admin actions | 1 | Python Dev | 2026-05-01 | 2026-05-01 | T11,T15 | Audit service and DB writes | Not Started
T17 | M5 | Refine validation messages, empty states, and desktop UX polish | 2 | UI Dev | 2026-05-02 | 2026-05-03 | T11,T15 | Improved usability | Not Started
T18 | M5 | Add centralized exception handling and logging | 1 | Python Dev | 2026-05-04 | 2026-05-04 | T16 | Stability layer | Not Started
T19 | M5 | Prepare future-extension hooks: settings, module registry, service interfaces | 2 | Architect/Dev | 2026-05-05 | 2026-05-06 | T15 | Extensibility baseline | Not Started
T20 | M6 | Create unit/integration test suite for auth and RBAC | 2 | QA/Dev | 2026-05-07 | 2026-05-08 | T18 | Automated tests | Not Started
T21 | M6 | Package desktop app and validate deployment checklist | 2 | Release Eng | 2026-05-09 | 2026-05-10 | T20 | Installable desktop build | Not Started
T22 | M6 | Prepare handover guide, admin manual, and release notes | 1 | BA/QA | 2026-05-11 | 2026-05-11 | T21 | Release documentation | Not Started
Formulas:
Planned Start = [Planned End, row above]+1
Planned End = [Planned Start]+[Effort (days)]-1

## Prompts
Incremental Development Prompts
Prompt ID | Phase | Goal | Copy/Paste Prompt | Expected Output | Dependency
P01 | Foundation | Architecture and folder structure | Act as a senior Python desktop architect. Design a modular desktop application using PySide6, PostgreSQL, and Liquibase. Propose a clean folder structure with presentation, application, domain, infrastructure, and tests. Include configuration strategy, dependency boundaries, and packaging considerations for future extensibility. | Architecture note, folder structure, module responsibilities, bootstrap guidance | -
P02 | Foundation | Screen map and UX baseline | Act as a desktop UX engineer. Define the complete screen list for an authentication + RBAC administration app in PySide6. Include login, dashboard, user management, role management, permission management, and audit log screens. For each screen, describe layout, key widgets, validation feedback, and navigation flow. | Screen inventory and UX specification | P01
P03 | Foundation | Normalized PostgreSQL schema | Design a normalized PostgreSQL schema for a desktop application that supports login by username or mobile number, secure password storage, multiple roles per user, configurable permissions, audit logs, sessions, and future extensibility. Provide tables, columns, PK/FK, unique constraints, indexes, and a relationship explanation. | DDL-ready schema design and ERD-style explanation | P01
P04 | Foundation | Liquibase changelog baseline | Generate a Liquibase migration plan and sample changelog structure for the RBAC desktop application schema. Organize changesets for users, login identifiers, credentials, roles, permissions, user-role mapping, role-permission mapping, sessions, audit logs, and settings. Include rollback guidance. | Liquibase changelog plan with ordered changesets | P03
P05 | Core Build | Project scaffold and bootstrap | Create a Python project scaffold for the desktop application. Use PySide6 for UI, SQLAlchemy for data access, and configuration files/environment variables for runtime settings. Show startup flow, dependency injection approach, and placeholders for Liquibase execution before app startup. | Starter project files and bootstrap code | P01,P04
P06 | Core Build | Login UI implementation | Build a PySide6 login window for a desktop application where the user can sign in using either username or mobile number and a password. Include polished layout, validation messages, show/hide password, loading state, and clean separation between UI and auth service calls. | Login screen code with reusable widgets | P02,P05
P07 | Core Build | Authentication service | Implement a Python authentication service for PostgreSQL-backed desktop software. Requirements: lookup by normalized username or mobile, verify secure password hash, reject inactive or locked accounts, update last login, increment failed attempts, and support temporary lockout. Provide service code and repository contracts. | Auth service, repository methods, and security flow | P03,P05
P08 | Core Build | Role and permission domain logic | Implement the Python domain and service layer for roles, permissions, user-role assignment, and role-permission mapping. The design must allow new roles and permissions to be added or modified without code changes to core models. Include validation rules and service interfaces. | RBAC service classes and business rules | P03,P05
P09 | Admin & Security | User management module | Create a user management module in PySide6 with create, update, activate, deactivate, and role assignment capabilities. The module must integrate with the RBAC service layer and keep UI logic separate from persistence logic. Include table view, form dialog, and validation guidance. | User admin UI and workflow design/code | P06,P08
P10 | Admin & Security | Role and permission administration UI | Create PySide6 screens for role management and permission mapping. Requirements: list roles, create/update role, view permission catalog, assign/unassign permissions to roles, and protect system roles from unsafe deletion. Provide a maintainable UI architecture and sample code. | Role/permission admin screens and interaction patterns | P08,P09
P11 | Admin & Security | RBAC enforcement | Show how to enforce role-based permissions consistently in a Python desktop application. Include navigation guards, button/action enablement, service-layer authorization checks, and a strategy to keep permission codes centralized and testable. | Permission guard pattern and enforcement examples | P08
P12 | Hardening | Audit logging and observability | Implement an audit logging strategy for a desktop application with authentication and RBAC. Capture login success/failure, user changes, role changes, permission changes, and settings updates. Provide PostgreSQL persistence approach, service hooks, and a simple audit viewer design. | Audit service design and integration points | P07,P08
P13 | Hardening | Error handling and UX polish | Improve the desktop application's usability and resilience. Propose standardized validation messages, exception handling, retry-safe database error messages, empty states, confirmation dialogs, and form behavior patterns appropriate for a professional business desktop application. | UX hardening checklist and reusable patterns | P06,P09,P10
P14 | Release | Testing strategy | Design a test strategy for the Python desktop application. Cover unit tests for auth and RBAC logic, integration tests for PostgreSQL repositories, migration verification for Liquibase, and UI smoke tests for primary screens. Include what to automate in CI. | Test plan, test matrix, and example test cases | P07,P08,P10
P15 | Release | Packaging and release prep | Explain how to package a PySide6 desktop application for distribution with PostgreSQL connectivity requirements. Include environment configuration, Liquibase migration execution strategy, secure secret handling, installer considerations, logging locations, and release checklist. | Packaging plan and release checklist | P05,P14
P16 | Future Ready | Extension planning | Propose an extension strategy for the Python desktop application so future modules can be added with minimal rework. Include module registration, settings management, permission expansion, migration discipline, event hooks, and coding standards for future teams. | Future extension blueprint and governance guidance | P01,P08,P12